## Sheet1
Sr. No. | Task list | Responsible | Start date | End date | Days | Status | Remarks
2017-08-01
1 | Set kick-off meeting | Asama,Akanksha,Nikita,Shruti | 2017-08-01 | 2017-08-01 | 1 | Completed | ü
2 | Agree on objectives | Asama,Akanksha,Nikita,Shruti | 2017-08-02 | 2017-08-03 | 1 | Completed | ü
| Requirement Gathering | [5 empty] | ü
3 | Define Scope | Shruti,Asama | 2017-08-04 | 2017-08-05 | 1 | Completed | ü
4 | Define Abstract | Ankita,Mohini | 2017-08-05 | 2017-08-06 | 1 | Completed | ü
5 | Define software requirements | Teju,Neha | 2017-08-06 | 2017-08-07 | 1 | Completed | ü
6 | Define hardware requirements | Teju,Neha | 2017-08-07 | 2017-08-08 | 1 | Completed | ü
7 | Define resource plan | Mohini,Ankita | 2017-08-08 | 2017-08-10 | 2 | Completed | ü
8 | Finalise SRS | Teju,Ankita,Mohini | 2017-08-10 | 2017-08-12 | 2 | Completed | ü
Design
9 | Design ER diagram | Ankita,Mohini | 2017-08-12 | 2017-08-14 | 2 | Completed | ü
10 | Design Usecase | Neha,Teju | 2017-08-14 | 2017-08-18 | 4 | Completed | ü
11 | Design Class diagram | Mohini,Ankita | 2017-08-18 | 2017-08-22 | 4 | Completed | ü
12 | Design activity diagram | Mohini,Teju | 2017-08-22 | 2017-08-24 | 2 | Incomplete | û
13 | Design component diagram | Teju,Neha | 2017-08-24 | 2017-08-27 | 3 | Incomplete | û
14 | Design User Interface | Ankita,Mohini | 2017-08-27 | 2017-09-02 | 6 | Incomplete | û
Implementation
15 | User Interface Development | Neha,Ankita | 2017-09-02 | 2017-09-07 | 5 | Incomplete | û
16 | Database Development | Mohini,Neha | 2017-09-07 | 2017-09-10 | 3 | Incomplete | û
17 | Coding | Teju,Ankita,Mohini | 2017-09-10 | 2017-09-17 | 7 | Incomplete | û
18 | Development complete | Mohini,Ankita | 2017-09-17 | 2017-09-20 | 3 | Incomplete | û
Testing
19 | Unit testing | Ankita,Mohini | 2017-09-20 | 2017-09-22 | 2 | Incomplete | û
20 | Integration testing | Teju,Neha | 2017-09-22 | 2017-09-24 | 2 | Incomplete | û
21 | User Interface testing | Ankita,Mohini | 2017-09-24 | 2017-09-26 | 2 | Incomplete | û
22 | System testing | Teju,Mohini | 2017-09-26 | 2017-09-28 | 2 | Incomplete | û
23 | Configuration Testing | Mohini,Ankita,Teju | 2017-09-28 | 2017-09-30 | 2 | Incomplete | û
| Release |  | 2017-09-30 | 2017-09-30
2017-09-30